## Tracking
[15 empty] | Warning | Delta >= 5%
[15 empty] | On-tracked | Delta <5%
[9 empty] | PIC | Milestone | Start date (Plan) | End date (Plan) | Est (MH) OR SP | Target | Current Progress | Current Progress | Previous value | Delta | Note
Module | 1 | 1 | 0 | 0 | Common | Overall | Level | Item | PIC | Milestone | Start date (Plan) | End date (Plan) | Est (MH) OR SP | Target | Current Progress | Current Progress | Previous value | Delta | Note | Tu | We
[20 empty] | 24 | 25
MODULE | 1 | 0 | 0 | 0 | Common | Overall | Level | TASK 1 |  |  | 2-Apr | 15-Jun | 213.2 | 0.76 | 67% |  |  | -10%
MODULE | 1 | 1 | 0 | 0 | Module | 1.1 | 1 | MODULE 1 |  | PoM_M_1 | 2-Apr | 15-Jun | 129.7 | 0.74 | 70% |  |  | -3%
MODULE | 1 | 1 | 1 | 0 | SPEC | 1.1.1 | 2 | SPEC - action |  | PoM_M_1 | 2-Apr | 16-Apr | 65.9 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 1 | SPEC | 1.1.1.1 | 3 | SPEC - action | Lion | PoM_M_1 | 2-Apr | 6-Apr | 28 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 2 | SPEC | 1.1.1.2 | 3 | SPEC - action | Tiger | PoM_M_1 | 13-Apr | 14-Apr | 9.3 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 3 | SPEC | 1.1.1.3 | 3 | SPEC - action | Lion | PoM_M_1 | 13-Apr | 14-Apr | 5.6 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 4 | SPEC | 1.1.1.4 | 3 | SPEC - action |  | PoM_M_1 | 16-Apr | 16-Apr | 9.3 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 5 | SPEC | 1.1.1.5 | 3 | SPEC - action |  | PoM_M_1 | 16-Apr | 16-Apr | 5.6 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 1 | 6 | SPEC | 1.1.1.6 | 3 | SPEC - action | Cat | PoM_M_1 | 15-Apr | 15-Apr | 8 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 2 | 0 | SPEC | 1.1.2 | 2 | SPEC - action |  | PoM_M_1 | 17-Apr | 21-Apr | 16 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 2 | 1 | SPEC | 1.1.2.1 | 3 | SPEC - action |  | PoM_M_1 | 17-Apr | 21-Apr | 8 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 2 | 2 | SPEC | 1.1.2.2 | 3 | SPEC - action |  | PoM_M_1 | 17-Apr | 21-Apr | 8 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 3 | 0 | SPEC-CUS | 1.1.3 | 2 | SPEC-CUS - action |  | PoM_M_4 | 22-May | 26-May | 7.4 | 0.57 | 0% |  |  | -57% | waiting OEM feedback
MODULE | 1 | 1 | 3 | 1 | SPEC-CUS | 1.1.3.1 | 3 | SPEC-CUS - action | Lion | PoM_M_4 | 22-May | 22-May | 4.2 | 1 | 0% |  |  | -100% | blocked waiting input
MODULE | 1 | 1 | 3 | 2 | SPEC-CUS | 1.1.3.2 | 3 | SPEC-CUS - action | Tiger | PoM_M_4 | 25-May | 25-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 3 | 3 | SPEC-CUS | 1.1.3.3 | 3 | SPEC-CUS - action | Lion | PoM_M_4 | 25-May | 25-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 3 | 4 | SPEC-CUS | 1.1.3.4 | 3 | SPEC-CUS - action |  | PoM_M_4 | 26-May | 26-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 3 | 5 | SPEC-CUS | 1.1.3.5 | 3 | SPEC-CUS - action |  | PoM_M_4 | 26-May | 26-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 3 | 6 | SPEC-CUS | 1.1.3.6 | 3 | SPEC-CUS - action | Cat | PoM_M_4 | 26-May | 26-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 4 | 0 | SPEC-CUS | 1.1.4 | 2 | SPEC-CUS - action |  | PoM_M_4 | 27-May | 29-May | 1.3 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 4 | 1 | SPEC-CUS | 1.1.4.1 | 3 | SPEC-CUS - action |  | PoM_M_4 | 27-May | 29-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 4 | 2 | SPEC-CUS | 1.1.4.2 | 3 | SPEC-CUS - action |  | PoM_M_4 | 27-May | 29-May | 0.6 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 5 | 0 | Code | 1.1.5 | 2 | Code - action |  | PoM_M_2 | 14-Apr | 25-May | 20.5 | 0.45 | 45% |  |  | 0%
MODULE | 1 | 1 | 5 | 1 | Code | 1.1.5.1 | 3 | Code - action | Cat | PoM_M_2 | 14-Apr | 16-Apr | 9.3 | 1 | 100% |  |  | 0%
MODULE | 1 | 1 | 5 | 2 | Code | 1.1.5.2 | 3 | Code - action | Tiger | PoM_M_2 | 25-May | 25-May | 2.8 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 5 | 3 | Code | 1.1.5.3 | 3 | Code - action | Cat | PoM_M_2 | 25-May | 25-May | 2.8 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 5 | 4 | Code | 1.1.5.4 | 3 | Code - action |  | PoM_M_2 | 25-May | 25-May | 2.8 | 0 | 0% |  | 9.3333 | 0%
MODULE | 1 | 1 | 5 | 5 | Code | 1.1.5.5 | 3 | Code - action | Cat | PoM_M_2 | 25-May | 25-May | 2.8 | 0 | 0% |  |  | 0%
MODULE | 1 | 1 | 5 | 6 | Code | 1.1.5.6 | 3 | Code - action | Cat | PoM_M_2 | 25-May | FALSE | 2.8 | 0 | 0% |  | 4 | 0%